## Sheet1
4A's Workshop - Structuring Agency Functions: The Intersection of Account, Project, and Production Managements
McCann - April 23, 2014
PAGE 1
"WHAT'S YOUR CHALLENGE?"
4A's - CONFIDENTIAL - NOT FOR DISTRIBUTION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
A lot of overlap in Traffic / Production / PM Groups .. Too many out-of-scope projects … Less people - less time … Recruiting and resourcing. | Finding $$$ to justify PM | Roles and responsibilities are unclear "Everybody touches everything" | Managing long-term project-based assignments ... Managing staff resources / proper utilization | Managing hours on client assignments … Educating / training staff to better manage client expectations. | Visibility and Forecasting … Talent at the right price and finding the right people … Balancing freelance and full-time staff … Training - integration issues | Consistency across several agency offices | Getting PM included in client SOWs | We do integration well, but still trying to manage our departments better, for example, we provide digital content but don't understand other aspects that we should ... All Production reports into me … Justifying costs to clients (since things should be cheaper!) ... Union issues .. "What is / isn't a commercial?" ... NO PMs! I think they are necessary since all jobs are now 360 campaigns. | Resource Mgt. - day-to-day staffing challenges … Managing freelancers and outside partners | Defining roles, processes, and workflow. | How to scale PMs as the company grows | Trying to scale PM with Production - dealing with the overlap | Went to "Digital First" without defining it. We are transitioning now | Overlap in PM & AM roles. Clients have been slow on digital … educating clients on digital. | We wear multiple hats … but how many hats can 1 person wear?
Managing overlap |  |  |  |  | We are a small agency, becoming bigger & developing new processes … We have visions and are doing it all at once … We integrated PM over the last year - differentiated PMs / Producers - developed Producer Hybrids … PMs are client-facing ... PMs will be replacing Ass't AEs ... We have had no issues getting PMs into SOWs - clients are OK with the role. | PMs not brought in briefings early enough … Conflicts with AMs and Creatives … PM overlap with Production. | Cross-training people; i.e., "Is it a commercial or not a commercial?" … Keeping costs in check … Legal is a huge issue .. SOWs are not developed enough - clients need to be more open ... Faster timelines. | Educating teams on how to better communicate internally and with clients; i.e. "Why things cost so much?" | Scheduling clients' needs … We have been good at integration, for example, Broadcast Producers are working with our Website Developers. | Balancing costs for what clients want to pay - more for less! … Managing both client and client procurement expectations, - trying to deliver projects at defined price points. | Last minute work …. Bringing in the right freelancers on project work … Bandwidth issues - not enough time or people. |  | Same as above … "Traditional" staff having difficulty adjusting now. Getting PMs involved earlier in projects assignments. Overlap in PM & AM, especially in junior roles. | Operations … PM, Digital Prod., Print Prod …. Integrating PMs into SOW. Clients see PM as an additional layer.
[9 empty] | AM vs. PM is polarizing across the board … it becomes who does it well and what is the need? Digital definitely needs PMs but not Broadcast, for example ... But there is so much overlap which leads into Production … for example Integrated Digital PMs and Digital Producers ... Project-based work is all about resource management ... being proactive and not reactive. |  | Overlapping role … Do more with less |  |  | Clients want us to do everything for them with less people … We are working with "expanded teams" … Managing people and workflow.
4A's Workshop - Structuring Agency Functions: The Intersection of Account, Project, and Production Managements
McCann - April 23, 2014
PAGE 2
TOPIC - AGENCY ORGANIZATION / MANAGING OVERLAP
4A's - CONFIDENTIAL - NOT FOR DISTRIBUTION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
PMs don't have the technical background that Producers have, however many Producers do have PM experience ... ALTERNATIVE MODEL - Organize at the project and not at the client level; i.e., the Restaurant Analogy, servicing the (1) Burger Bar or (2) Tasting Menu or (3) Full Dinner? | A Producer can be an expert in their discipline, but can't necessarily manage other "integrated" projects. | PMs need a clarity in their roles and responsibilities to do their jobs - it sends a wrong message when there are dual roles; i.e., Ass't AEs. | Bringing in Jr-level Project Coordinators - then in 3-5 years will move either into AM or PM role … A PM in the agency world is totally different than a PM in the business world … Clear direction, but based in legacy structures is quantifiable ... Build more cutomized solutions. |  | Our Producers handle the technical aspects of a project - they don’t want to manage workflow … Advocates separating PM from Producers … Evolution of Ass't AEs was traffic - now it's PM. We've moved into a stepped approach toward nurturing these people ... Focus is on the strategy of business vs the strategy of tactics. |  | Is Integrated Production (Hybrid PM & Producer combined) a staffing structure? The new future? | I am the product of being a hybrid Producer … Supports Hybrid producer roles … We become the ones to ensure that things don’t fall through the cracks, especially since we work on a limited number of projects at any one time ... Agency has no Art Buyers - Producers do it. Art buyers need to learn other disciplines. | The Producer tells a creative story … they need an new language and a new rolodex … Producers are not looking to embrace the hybrid. |  | Mostly digital shop supports separate AM and PM roles … We do not have a need for a F.T. Producer. | AMs can't hide behind the PM. They need to be more strategic … Even a small shop needs Sr. PMs who must be on par with their AM counterparts … Production and PM mix didn’t work. | Ass't AEs now moved into PM - worried that in 3-4 years from now some people won’t understand the brand at all … worried about a "lost generation" where many PMs will be less strategic in their thinking. | True PMs are now just Digital … Traffic became "Project Coordinators" under PM dept. Used to be a 1-year turnaround, but now they can stay on longer with PM and can pick their career paths either in AM or PM.
We are putting a renewed focus on our AMs. Now all AMs own the client's business. Jr AEs are now ready sales reports. Key is early training! ... If anything, we rely on PMs too much; i.e., PM prepared the project status schedule but AMs really need to know the schedule ... Eliminate layers - if a Digital Producer is on the assignment, then no PM - the Producer replaces the PM. | [6 empty] | Art Buying is on the front line of integration. Many agencies still have Art Buying roles. Art Buyers have Art Producer titles. |  | It is difficult if you are trying to integrate disciplines - Digital PMs & Digital Producers feel like they'll go in reverse if taking on offline projects too …. In most Digital shops, Digital Producers do it all - AM/ PM/ Producer. |  |  |  | Our PMs coordinate the tasks and our Producers are the technical experts - they are separate, not integrated positions … PMs titles include "Engagement Managers" - they manage the projects and are client-facing … AMs work on Sales and Business Development.
It depends on an individual's skills if they will be trained as an AM or PM; i.e., are they capable of managing creatives?
4A's Workshop - Structuring Agency Functions: The Intersection of Account, Project, and Production Managements
McCann - April 23, 2014
PAGE 3
TOPIC - AGENCY ORGANIZATION / INTEGRATED PRODUCTION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
4A's - CONFIDENTIAL - NOT FOR DISTRIBUTION
Agency has a "Content Team" too staffed with 4-41/2 dedicated people (2 creatives, social strategist, AM, and may bring in a specialist as needed - it has been very successful … Sold the idea to clients local / social programs and bill service as a monthly fee ... Found someone right out of school that had an interest in film. | The PM should coordinate team meetings. |  | Models - (1) Individual Producers report to a Producers' group (2) Hybrid Producer … With regard to Community Mgt. discussion - agrees that typical for agencies to train clients who then take it in-house - not a surprise since it's customer service ... With regard to operating a LAB, the agency tried several years ago but had no success - clients weren't being billed. |  |  |  | Although Digital Business Affairs people are hard to find, we are having great successes in cross-training staff … Art Buyers are working more closely with the Broadcast Group. | Many Producers are "specialists" - subject matter experts, so get them involved with creative briefs early in the planning stages so they may be able to identify issues that might otherwise be overlooked. | AMs and PMs may coordinate team meetings - however since some clients have assigned PMs and some don't - we have no unified process; i.e., sometimes AMs - sometimes PMs. | We also have an on-boarding process for new staff. |  |  | We are evolving to Integrated Production solutions. | Our agency is dedicated to training. | For new staff, regardless of their backgrounds and experience, we are very clear in outlining our agency processes.
|  |  | With regard to legal approvals, the agency routes everything through a Business Affairs Group and relies heavily on external counsel. |  |  |  | "Always on" drives us crazy! It's often extremely difficult to get legal approval for an immediate release - A tweet can come back to haunt you. Better get legal! … | We are restructuring to an Integrated Producer Model, where Producers do everything - it's been hardest on Broadcast … Producers are responsible for managing all aspects of the project … | Communication is important! We encourage broad team participation ... We have an on-boarding process for new people to introduce them to all staff members.
[7 empty] | Digital Production Agreements are especially difficult to get through ... Agency gives internal presentations on legal risks to staff on a regular basis. | Because everything is evolving so fast, Creatives have become accustomed to this change … Agency has a "Content Lab" for Community Mgt. / Social Media - NOT "always on" but fast turnaround with a small group of people (Newsroom too - but clients not paying appropriately for it). | Agency has an "Always On" Team - well-funded for a small group. Clients typically take Community Mgt. in-house … We are structured for Integrated Production.
4A's Workshop - Structuring Agency Functions: The Intersection of Account, Project, and Production Managements
McCann - April 23, 2014
PAGE 4, continued
TOPIC - AGENCY ORGANIZATION / INTEGRATED PRODUCTION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
4A's - CONFIDENTIAL - NOT FOR DISTRIBUTION
[8 empty] | We have a Lab that makes things. It includes "Product Architects" ... We have a Digital Studio too that includes Digital Creatives - we tap into Producers as needed ... We are evolving to "Integrated Creatives". | Looks at it from the creative point of view and it's really on a case-by-case basis … Project briefs evolve into the final deliverable, or maybe 8 or 10 deliverables … Adding Creative people in may not be financially advantageous, but from a creative standpoint it may be absolutely necessary ... Being open to being open. |  | Has a group of creatives turning out content on a daily basis - Client Procurement is a constant problem and makes it difficult to make a profit on it. |  |  | We use a lot of Interns - they typically are smart, know a lot, and can flip on a dime.
4A's Workshop - Structuring Agency Functions: The Intersection of Account, Project, and Production Managements
McCann - April 23, 2014
PAGE 5
TOPIC - Managing in a Project-Based Environment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
4A's - CONFIDENTIAL - NOT FOR DISTRIBUTION
Educating AM staff helps … (1) Educate your clients! … (2) Include Ass't AE's; i.e., how to manage hours, financials, etc. … Ref: PM Software - we're using Advantage Blue - works well for us. |  | With regard to resource management tools - they should not become the job! … Simplify the process - don’t expect 100% accuracy. | The dilemma is managing resources - how do you stay nimble enough to find resources to work on a "one-off" project? … Ref: Workamajig PM Software (working with them to develop more short-term project tracking) |  | Ref: Workamajig PM Software … Look for open-sourced systems that you can use to export data and work with it … We also use Advantage software. | How to handle scope creep? - especially with Digital, we use a phased approach - it's more precise as you go along. | Re: Resource Managers - we eliminated ours (that's the role I've taken on now). | We have a "Spot Team" made up of mid-level people for "one-off" project work. .. Ref: Clarizen PM Software | A good resource management tool is important … Key however is the process - not the tool, you need to layer the tool on the process (most tools are pretty "clunky" - Excel may be basic - but people understand it)… ref: AtTask PM Software | You need to tap into freelance … SOW maintenance and monitoring is important. | For project work, it's a calculated risk for excess vs. not having the staff to meet all needs - you've got to keep some people on the bench . | For pricing, we utilize a tiered rate structure; i.e., project mode has a 2nd pricing structure. | How to handle scope creep? - we use a phased approach too include a "Discovery Phase" … Re: Resource Managers - we eliminated ours (became a crutch for PMs). | How to handle scope creep? - SAME - we use a phased approach too include a "Discovery Phase"… ref: Vantage PM Software.
[8 empty] | How to handle scope creep? - We use a lot of change orders. | Re: Resource Managers - we have one (used primarily by the CFO's/COO's to tell them what's going on). |  | Ref: Workamajig too. Working with them on updating resource forecasting. |  | Re: Resource Managers - we eliminated ours (that's the role I've taken on now).
Quick Wrap-Up
AM/PM/Production Overlap: (1) Clearly define roles and responsibilities (2) Maintain separation
Integrated Production: (1) The future … Is every Producer a hybrid? Not necessarily! (2) Production needs to work as an Integrated Team
Tools: You may select a tool and use 10-20-30 % of it .. The key is to whatever you choose to use - use it well!
Project-Based Assignments: (1) Be nimble (2) Be flexible (3) Use "Smart Teams" (4) Staff to client / project needs